## About
Created on: | 24 Jun 22 18:57 UTC
Jira Site: | https://5sport.atlassian.net
Jira Query: | project = "QF" ORDER BY created DESC

## Your Jira Issues
Issue Type | Key | Summary | Assignee | Reporter | Priority | Status | Resolution | Created | Updated | Due date
Bug | QF-23 | Error from page 2 to 10 |  | Yulia | Medium | To Do |  | 2022-06-07 19:37 | 2022-06-07 19:37
Bug | QF-22 | Menu bar in item "עוד" NBA |  | Irena Weitzman | Medium | To Do |  | 2022-06-03 14:45 | 2022-06-03 14:45 | 2022-06-03
Bug | QF-21 | Different language in menu bar |  | Irena Weitzman | High | To Do |  | 2022-06-03 14:37 | 2022-06-03 14:37 | 2022-06-03
Bug | QF-20 | Language in Global item (NBA) |  | Irena Weitzman | Medium | To Do |  | 2022-06-03 14:30 | 2022-06-05 16:30 | 2022-06-03
Bug | QF-19 | Language in NBA |  | Irena Weitzman | Medium | To Do |  | 2022-06-03 14:23 | 2022-06-03 14:23 | 2022-06-03
Bug | QF-18 | No information in "פוטבול" |  | Irena Weitzman | Medium | To Do |  | 2022-06-03 14:13 | 2022-06-05 16:22 | 2022-06-03
Bug | QF-17 | Sign "5" without color |  | Irena Weitzman | Medium | To Do |  | 2022-06-03 14:05 | 2022-06-03 14:05 | 2022-06-03
Bug | QF-16 | Same color |  | Irena Weitzman | Low | To Do |  | 2022-06-03 14:00 | 2022-06-03 14:00 | 2022-06-03
Bug | QF-15 | Link with underline |  | Irena Weitzman | Low | To Do |  | 2022-06-03 13:46 | 2022-06-03 13:46
Bug | QF-14 | Text is not visible |  | Yulia | Medium | To Do |  | 2022-06-02 18:53 | 2022-06-02 18:53
Bug | QF-13 | Search text not properly aligned |  | Yulia | Low | To Do |  | 2022-06-02 18:46 | 2022-06-02 18:46
Bug | QF-12 | 5Radio not properly alighted |  | Yulia | Medium | To Do |  | 2022-06-02 18:01 | 2022-06-07 19:31
Bug | QF-11 | No contact information |  | Yulia | Low | To Do |  | 2022-06-02 17:51 | 2022-06-02 17:51
Bug | QF-10 | Comment section icon is not clickable |  | Yulia | Low | To Do |  | 2022-06-02 17:48 | 2022-06-02 17:48
Bug | QF-9 | Search results - wrong icon for mouse |  | Yulia | Medium | To Do |  | 2022-06-02 17:38 | 2022-06-02 17:38
Bug | QF-8 | Relevant search results |  | Yulia | Medium | To Do |  | 2022-06-02 16:41 | 2022-06-07 19:29
Bug | QF-7 | On/Off button wrong behavior |  | Yulia | Low | To Do |  | 2022-06-02 16:23 | 2022-06-02 16:23
Bug | QF-6 | The end of the website |  | Irena Weitzman | High | To Do |  | 2022-06-01 20:32 | 2022-06-05 16:23 | 2022-06-01
Bug | QF-5 | No information about a match |  | Irena Weitzman | High | To Do |  | 2022-06-01 20:25 | 2022-06-01 20:25 | 2022-06-01
Bug | QF-4 | Loading sign "5" |  | Irena Weitzman | Low | To Do |  | 2022-06-01 20:19 | 2022-06-01 20:19 | 2022-06-01
Bug | QF-3 | Footer |  | Irena Weitzman | Low | To Do |  | 2022-06-01 20:09 | 2022-06-01 20:09 | 2022-06-01
Bug | QF-2 | Visual glitches |  | Irena Weitzman | High | To Do |  | 2022-06-01 09:23 | 2022-06-01 09:23 | 2022-06-01
Bug | QF-1 | Screen center alignment |  | Yulia | Low | To Do |  | 2022-06-01 09:11 | 2022-06-02 16:13 | 2022-06-08